## Sheet1
1.0 Implementing Technology into a SME
1.1 Database Creation |  |  | 1.2 HR System |  |  |  | 1.3 Website Development |  |  | 1.4 IT Training |  |  | 1.5 Project Management
| 1.1.1 Create Tables |  |  | 1.2.1 Plan System |  |  |  | 1.3.1 Plan Website |  |  | 1.4.1 Plan Material |  |  | 1.5.1 Initiate Project
|  | 1.1.1.1 Identify Primary Key |  | 1.2.2 Create System |  |  |  | 1.3.2 Design Website |  |  | 1.4.2 Prepare Material |  |  | 1.5.2 Plan Project
|  | 1.1.1.2 Identify Data Types | [9 empty] | 1.4.2.1 Create Word Doc
|  |  |  | 1.2.3 Test System |  |  |  | 1.3.3 Trial Website |  |  |  | 1.4.2.2 Create PowerPoint |  | 1.5.3 Execute Project
1.1.2 Create Forms
[5 empty] | 1.2.3.1 Trial |  |  |  | 1.3.3.1 Analyse Traffic |  | 1.4.3 Print Material |  |  | 1.5.4 Monitor and Control Project
| 1.1.3 Test Database |  |  |  | 1.2.3.2 Adjustments |  |  |  | 1.3.3.2 Review Traffic
[11 empty] | 1.4.4 Organise Training Sessions |  |  | 1.5.5 Close Project
1.2.4 Install System
1.4.5 Exceute Training Sessions